## Broker Portal Project Plan
WBS | Workstream | Task Name | Deliverable / Exit Criteria | Start Date | End Date | Workdays | Owner | Dependencies | Requirement / Decision IDs | Phase Gate | Status | % Complete | Implementation Notes | Milestone
0.1 | Discovery & Governance | Confirm executive sponsor and product ownership | Named accountable sponsor, product owner and decision rights | 2026-10-01 | 2026-10-02 | 2 | Program Manager | - |  | Gate 0 | Not Started | 0% |  | No
0.2 | Discovery & Governance | Approve project charter and scope boundaries | Signed charter covering four modules and Duck Creek system-of-record boundary | 2026-10-01 | 2026-10-05 | 3 | Sponsor / Product Owner | 0.1 |  | Gate 0 | Not Started | 0% |  | No
0.3 | Discovery & Governance | Establish governance forums and cadence | SteerCo, architecture, security, data, AI governance and change-control calendar | 2026-10-02 | 2026-10-06 | 3 | Program Manager | 0.1 |  | Gate 0 | Not Started | 0% |  | No
0.4 | Discovery & Governance | Baseline stakeholder and persona map | External Broker, Broker Admin, Underwriter, Operations, Guideline Admin, Support personas approved | 2026-10-02 | 2026-10-07 | 4 | Business Architect | 0.1 |  | Gate 0 | Not Started | 0% |  | No
0.5 | Discovery & Governance | Confirm Release 1 product, state and journey scope | OD-001 decision recorded with explicit inclusions and exclusions | 2026-10-05 | 2026-10-09 | 5 | Product Owner | 0.2 | OD-001 | Gate 0 | Not Started | 0% |  | No
0.6 | Discovery & Governance | Discover Duck Creek products, versions and services | API catalogue, environments, authentication, limits and owners documented | 2026-10-05 | 2026-10-16 | 10 | Integration Architect | 0.2 | OD-002,OD-009 | Gate 0 | Not Started | 0% |  | No
0.7 | Discovery & Governance | Confirm broker and producer source of truth | Authority and synchronization model approved | 2026-10-05 | 2026-10-12 | 6 | Data Architect | 0.2 | OD-003 | Gate 0 | Not Started | 0% |  | No
0.8 | Discovery & Governance | Confirm Auth0 tenant and federation policies | Tenant, organizations, connections, MFA, session and invitation policies approved | 2026-10-05 | 2026-10-12 | 6 | IAM Architect | 0.2 | OD-004 | Gate 0 | Not Started | 0% |  | No
0.9 | Discovery & Governance | Confirm AI platform and content services | Model, search/vector, repository, moderation and retention services approved | 2026-10-05 | 2026-10-14 | 8 | AI Architect | 0.2 | OD-005 | Gate 0 | Not Started | 0% |  | No
0.1 | Discovery & Governance | Approve guideline content governance | Owners, reviewers, effective dating, supersession and emergency correction workflow approved | 2026-10-08 | 2026-10-15 | 6 | Underwriting Product Owner | 0.4 | OD-006 | Gate 0 | Not Started | 0% |  | No
0.11 | Discovery & Governance | Approve moratorium operating model | Authority, scope, precedence, exceptions, communications, lifting and fail-safe decisions approved | 2026-10-08 | 2026-10-16 | 7 | Business Operations Lead | 0.4 | OD-007,OD-008 | Gate 0 | Not Started | 0% |  | No
0.12 | Discovery & Governance | Set NFR baselines and support model | Approved SLOs, volumes, RTO/RPO, retention, support hours and browser matrix | 2026-10-08 | 2026-10-16 | 7 | Solution Architect | 0.4 | OD-010,NFR-001,NFR-002,NFR-003,NFR-008,NFR-011 | Gate 0 | Not Started | 0% |  | No
0.13 | Discovery & Governance | Create requirement traceability baseline | All 68 functional/NFR requirements mapped to increments, tests and owners | 2026-10-12 | 2026-10-20 | 7 | Lead BA | 0.5,0.6,0.8,0.9,0.10,0.11,0.12 |  | Gate 0 | Not Started | 0% |  | No
0.14 | Discovery & Governance | Gate 0: Discovery and scope approval | SteerCo approves scope, architecture discovery plan and delivery baseline | 2026-10-21 | 2026-10-21 | 1 | Steering Committee | 0.13 |  | Gate 0 | Not Started | 0% |  | Yes
1.1 | Architecture & Platform | Define target logical architecture | Approved context, container and component views for portal, APIs, data and integrations | 2026-10-12 | 2026-10-23 | 10 | Solution Architect | 0.6,0.7,0.8,0.9 |  | Gate 1 | Not Started | 0% |  | No
1.2 | Architecture & Platform | Define modular application boundaries | Module ownership, contracts and deployment boundaries approved | 2026-10-19 | 2026-10-27 | 7 | Solution Architect | 1.1 | NFR-010 | Gate 1 | Not Started | 0% |  | No
1.3 | Architecture & Platform | Define canonical data model | Identity, guideline, moratorium, submission and operations domains modeled | 2026-10-19 | 2026-10-30 | 10 | Data Architect | 1.1 |  | Gate 1 | Not Started | 0% |  | No
1.4 | Architecture & Platform | Define API and error standards | Versioning, OAuth scopes, validation, Problem Details, pagination and payload standards | 2026-10-19 | 2026-10-27 | 7 | API Architect | 1.1 | NFR-004,NFR-007 | Gate 1 | Not Started | 0% |  | No
1.5 | Architecture & Platform | Threat model all four modules | Threats, mitigations, abuse cases and security backlog approved | 2026-10-19 | 2026-10-30 | 10 | Security Architect | 1.1 | NFR-004,NFR-005,NFR-012 | Gate 1 | Not Started | 0% |  | No
1.6 | Architecture & Platform | Define privacy and records controls | Classification, minimization, retention, deletion, legal hold and support-access rules | 2026-10-21 | 2026-10-30 | 8 | Privacy Lead | 1.3 | NFR-005 | Gate 1 | Not Started | 0% |  | No
1.7 | Architecture & Platform | Define accessibility and UX standards | WCAG 2.2 AA patterns, supported devices and design-system acceptance checklist | 2026-10-19 | 2026-10-27 | 7 | UX Lead | 0.12 | NFR-006,NFR-011 | Gate 1 | Not Started | 0% |  | No
1.8 | Architecture & Platform | Provision development and test environments | Dev, integration, QA, security, performance and UAT environments available | 2026-10-12 | 2026-10-30 | 15 | Cloud / DevOps Lead | 0.14 |  | Gate 1 | Not Started | 0% |  | No
1.9 | Architecture & Platform | Create repositories and branching strategy | Source repositories, ownership, branch protections and pull-request templates active | 2026-10-12 | 2026-10-16 | 5 | DevOps Lead | 0.14 | NFR-010 | Gate 1 | Not Started | 0% |  | No
1.1 | Architecture & Platform | Implement CI quality pipeline | Build, unit tests, linting, SAST, SCA and artifact versioning automated | 2026-10-19 | 2026-10-30 | 10 | DevOps Lead | 1.9 | NFR-004,NFR-010 | Gate 1 | Not Started | 0% |  | No
1.11 | Architecture & Platform | Implement CD and configuration promotion | Environment approvals, secret references, rollback and release evidence automated | 2026-10-26 | 2026-11-06 | 10 | DevOps Lead | 1.8,1.10 | NFR-004,NFR-010 | Gate 1 | Not Started | 0% |  | No
1.12 | Architecture & Platform | Build Angular portal shell | Responsive navigation, route framework, error boundary and design system implemented | 2026-10-26 | 2026-11-06 | 10 | Frontend Lead | 1.7,1.9 | NFR-006,NFR-011 | Gate 1 | Not Started | 0% |  | No
1.13 | Architecture & Platform | Build ASP.NET Core API foundation | API host, dependency injection, validation, correlation and standard errors implemented | 2026-10-26 | 2026-11-06 | 10 | Backend Lead | 1.4,1.9 | NFR-007,NFR-009,NFR-010 | Gate 1 | Not Started | 0% |  | No
1.14 | Architecture & Platform | Build SQL schema and migration baseline | Versioned schemas for core domains and deployment rollback scripts | 2026-10-26 | 2026-11-06 | 10 | DBA | 1.3,1.9 | NFR-010 | Gate 1 | Not Started | 0% |  | No
1.15 | Architecture & Platform | Implement observability foundation | Structured logs, traces, metrics, correlation IDs, health checks and dashboards | 2026-11-02 | 2026-11-13 | 10 | SRE Lead | 1.11,1.13 | NFR-009 | Gate 1 | Not Started | 0% |  | No
1.16 | Architecture & Platform | Gate 1: Architecture and platform readiness | Architecture, controls, environments and delivery pipelines approved | 2026-11-16 | 2026-11-16 | 1 | Architecture Review Board | 1.2,1.5,1.6,1.11,1.12,1.13,1.14,1.15 |  | Gate 1 | Not Started | 0% |  | Yes
2.1 | Identity & Access | Configure Auth0 tenant baseline | Applications, APIs, organizations, connections and environments configured | 2026-11-02 | 2026-11-13 | 10 | IAM Engineer | 0.8,1.8 | BR-AUTH-001,BR-AUTH-002,BR-AUTH-003 | Gate 2 | Not Started | 0% |  | No
2.2 | Identity & Access | Implement portal OIDC login and logout | Auth0-mediated login, callback, token handling and logout policy implemented | 2026-11-09 | 2026-11-20 | 10 | Frontend Lead | 1.12,2.1 | BR-AUTH-001,BR-AUTH-003,BR-AUTH-008 | Gate 2 | Not Started | 0% |  | No
2.3 | Identity & Access | Implement API token validation | Issuer, audience, signing, scope and expiry enforcement with safe errors | 2026-11-09 | 2026-11-20 | 10 | Backend Lead | 1.13,2.1 | BR-AUTH-001,BR-AUTH-005,BR-AUTH-008 | Gate 2 | Not Started | 0% |  | No
2.4 | Identity & Access | Implement organization and agency context | Organization, branch and producer context resolved and propagated server-side | 2026-11-16 | 2026-11-27 | 10 | IAM Engineer | 2.3,0.7 | BR-AUTH-004,BR-AUTH-005 | Gate 2 | Not Started | 0% |  | No
2.5 | Identity & Access | Implement RBAC and entitlement policy engine | Role, permission, product, agency and resource-ownership authorization enforced | 2026-11-23 | 2026-12-04 | 10 | Backend Lead | 2.4 | BR-AUTH-005 | Gate 2 | Not Started | 0% |  | No
2.6 | Identity & Access | Build broker invitation and administration UI | Invite, view, update, deactivate and role-change request flows scoped to agency | 2026-11-23 | 2026-12-04 | 10 | Frontend Lead | 2.2,2.4 | BR-AUTH-006 | Gate 2 | Not Started | 0% |  | No
2.7 | Identity & Access | Implement user lifecycle services | Invitation expiry, duplicate detection, JML, dormant account and revocation workflows | 2026-11-30 | 2026-12-11 | 10 | Backend Lead | 2.5,2.6 | BR-AUTH-006,BR-AUTH-008 | Gate 2 | Not Started | 0% |  | No
2.8 | Identity & Access | Implement Auth0/portal/Duck Creek provisioning adapter | Provisioning, partial-state handling, idempotency and downstream identifiers implemented | 2026-11-30 | 2026-12-18 | 15 | Integration Lead | 0.6,2.7 | BR-AUTH-007,BR-AUTH-010 | Gate 2 | Not Started | 0% |  | No
2.9 | Identity & Access | Implement MFA, session and recovery controls | MFA, lockout, timeout, recovery, token revocation and IdP outage behavior tested | 2026-11-23 | 2026-12-11 | 15 | Security Engineer | 2.1,2.2 | BR-AUTH-008 | Gate 2 | Not Started | 0% |  | No
2.1 | Identity & Access | Implement privileged access controls | Separation of duties, reason capture, time-bound support access and evidence implemented | 2026-12-07 | 2026-12-18 | 10 | Security Engineer | 2.5 | BR-AUTH-009 | Gate 2 | Not Started | 0% |  | No
2.11 | Identity & Access | Implement identity audit and reconciliation | Immutable lifecycle events, provisioning status, retries and reconciliation dashboard | 2026-12-14 | 2026-12-24 | 9 | SRE / IAM | 2.8,2.10 | BR-AUTH-009,BR-AUTH-010 | Gate 2 | Not Started | 0% |  | No
2.12 | Identity & Access | Execute identity contract and security tests | Federation, authorization boundaries, negative paths, revocation and recovery pass | 2026-12-14 | 2027-01-08 | 20 | QA / Security | 2.5,2.8,2.9,2.10 | BR-AUTH-001:BR-AUTH-010 | Gate 2 | Not Started | 0% |  | No
2.13 | Identity & Access | Gate 2: Platform and identity acceptance | Approved users authenticate; unauthorized and out-of-scope access is denied and auditable | 2027-01-11 | 2027-01-11 | 1 | Product Owner / Security | 2.11,2.12 |  | Gate 2 | Not Started | 0% |  | Yes
3.1 | Guideline Content & Search | Inventory and classify guideline sources | Authoritative documents, owners, sensitivity and applicability metadata catalogued | 2026-11-16 | 2026-11-27 | 10 | Guideline Product Owner | 0.10,1.6 | BR-AI-001,BR-AI-002 | Gate 3 | Not Started | 0% |  | No
3.2 | Guideline Content & Search | Design content repository and metadata schema | Version, product, state, class, coverage, owner, approval and effective-date model approved | 2026-11-23 | 2026-12-04 | 10 | Data / AI Architect | 1.3,3.1 | BR-AI-001,BR-AI-009 | Gate 3 | Not Started | 0% |  | No
3.3 | Guideline Content & Search | Build secure upload and malware scanning | Approved PDF, Word and spreadsheet upload with validation and quarantine | 2026-11-30 | 2026-12-11 | 10 | Backend Lead | 3.2,1.13 | BR-AI-001,NFR-004 | Gate 3 | Not Started | 0% |  | No
3.4 | Guideline Content & Search | Build extraction and normalization pipeline | Content extraction, unsupported-element reporting and quality status implemented | 2026-12-07 | 2026-12-18 | 10 | AI Engineer | 3.3 | BR-AI-001 | Gate 3 | Not Started | 0% |  | No
3.5 | Guideline Content & Search | Build chunking and secure indexing pipeline | Searchable chunks and indexes retain source/version/applicability and ACL metadata | 2026-12-14 | 2027-01-08 | 20 | AI Engineer | 3.4,0.9 | BR-AI-004,BR-AI-005,BR-AI-011 | Gate 3 | Not Started | 0% |  | No
3.6 | Guideline Content & Search | Build content review and approval workflow | Draft, review, approve, reject and publish states with separation of duties | 2026-12-07 | 2026-12-24 | 14 | Backend / Frontend | 3.2,2.5 | BR-AI-002,BR-AI-009 | Gate 3 | Not Started | 0% |  | No
3.7 | Guideline Content & Search | Build publication and supersession controls | Effective publication, retirement, supersession, emergency correction and audit history | 2026-12-21 | 2027-01-08 | 15 | Backend Lead | 3.5,3.6 | BR-AI-002,BR-AI-009 | Gate 3 | Not Started | 0% |  | No
3.8 | Guideline Content & Search | Build authorized search experience | Keyword/filter search by product, state, class, coverage and effective date | 2026-12-21 | 2027-01-15 | 20 | Frontend / AI | 3.5,2.5 | BR-AI-003,BR-AI-004 | Gate 3 | Not Started | 0% |  | No
3.9 | Guideline Content & Search | Test content lifecycle and access isolation | Publication gates, version retrieval and cross-scope leakage tests pass | 2027-01-11 | 2027-01-22 | 10 | QA / Security | 3.7,3.8 | BR-AI-001:BR-AI-005,BR-AI-009,BR-AI-011 | Gate 3 | Not Started | 0% |  | No
3.1 | Guideline Content & Search | Gate 3: Content and search acceptance | Approved content is searchable; draft, retired and unauthorized content is blocked | 2027-01-25 | 2027-01-25 | 1 | Guideline Product Owner | 3.9 |  | Gate 3 | Not Started | 0% |  | Yes
4.1 | AI Guideline Assistant | Define assistant prompts and response contract | Answer, evidence, applicability, limitation, next action and notice schema approved | 2027-01-04 | 2027-01-15 | 10 | AI Product Owner | 0.9,0.10 | BR-AI-003:BR-AI-007,BR-AI-012 | Gate 4 | Not Started | 0% |  | No
4.2 | AI Guideline Assistant | Build retrieval orchestration with entitlement filters | ACL filtering precedes retrieval and generation for every query | 2027-01-11 | 2027-01-29 | 15 | AI Engineer | 3.5,2.5,4.1 | BR-AI-003,BR-AI-004,BR-AI-011 | Gate 4 | Not Started | 0% |  | No
4.3 | AI Guideline Assistant | Build grounded answer generation | Answers use approved retrieved evidence and preserve applicability/version context | 2027-01-18 | 2027-02-05 | 15 | AI Engineer | 4.2 | BR-AI-004,BR-AI-005 | Gate 4 | Not Started | 0% |  | No
4.4 | AI Guideline Assistant | Implement citation rendering and source navigation | Document, locator, version and effective date displayed and accessible | 2027-01-25 | 2027-02-05 | 10 | Frontend Lead | 3.8,4.3 | BR-AI-005 | Gate 4 | Not Started | 0% |  | No
4.5 | AI Guideline Assistant | Implement refusal and escalation flow | Missing, conflicting, stale or ambiguous evidence produces bounded refusal and owner escalation | 2027-02-01 | 2027-02-12 | 10 | AI / Frontend | 4.3 | BR-AI-006,BR-AI-007 | Gate 4 | Not Started | 0% |  | No
4.6 | AI Guideline Assistant | Implement disclaimer and feedback capture | Informational-use notice plus usefulness, issue category and comments captured | 2027-02-01 | 2027-02-12 | 10 | Frontend Lead | 4.3 | BR-AI-008,BR-AI-012 | Gate 4 | Not Started | 0% |  | No
4.7 | AI Guideline Assistant | Implement privacy-safe interaction records | Question, sources, response, feedback and correlation retained under policy | 2027-02-01 | 2027-02-12 | 10 | Backend Lead | 1.6,4.3 | BR-AI-010 | Gate 4 | Not Started | 0% |  | No
4.8 | AI Guideline Assistant | Implement prompt-injection and disclosure defenses | Document and user-input attacks, unauthorized retrieval and sensitive output controls implemented | 2027-02-01 | 2027-02-19 | 15 | AI Security Engineer | 4.2,4.3 | BR-AI-011,NFR-012 | Gate 4 | Not Started | 0% |  | No
4.9 | AI Guideline Assistant | Create representative AI evaluation set | Eligibility, appetite, exclusions, limits and geographic questions with expected evidence | 2027-01-18 | 2027-02-05 | 15 | Underwriting SMEs | 3.1,4.1 | NFR-012 | Gate 4 | Not Started | 0% |  | No
4.1 | AI Guideline Assistant | Automate AI quality evaluation | Groundedness, citation correctness, relevance, refusal, boundary and latency measures gated | 2027-02-08 | 2027-02-19 | 10 | AI QA Lead | 4.3,4.5,4.8,4.9 | NFR-002,NFR-012 | Gate 4 | Not Started | 0% |  | No
4.11 | AI Guideline Assistant | Implement configuration lineage and rollback | Prompt, model, ranking, chunking and policy changes versioned and reversible | 2027-02-08 | 2027-02-19 | 10 | MLOps Lead | 4.1 | NFR-010,NFR-012 | Gate 4 | Not Started | 0% |  | No
4.12 | AI Guideline Assistant | Execute red-team and privacy testing | Prompt injection, exfiltration, content poisoning and retention tests pass | 2027-02-22 | 2027-03-05 | 10 | Security / Privacy | 4.8,4.10,4.11 | BR-AI-011,NFR-005,NFR-012 | Gate 4 | Not Started | 0% |  | No
4.13 | AI Guideline Assistant | Gate 4: AI assistant acceptance | Citation-backed assistant meets approved quality thresholds and safe-failure rules | 2027-03-08 | 2027-03-08 | 1 | AI Governance Board | 4.4,4.5,4.6,4.7,4.12 |  | Gate 4 | Not Started | 0% |  | Yes
5.1 | Moratorium Management | Approve detailed moratorium decision model | Activities, scope dimensions, precedence, in-flight treatment, exceptions and fail-safe policy signed | 2026-11-16 | 2026-12-04 | 15 | Business Operations Lead | 0.11 | BR-MOR-001:BR-MOR-016 | Gate 5 | Not Started | 0% |  | No
5.2 | Moratorium Management | Design effective-dated scope and version model | Product, geography, peril, coverage, risk, distribution and period schema approved | 2026-11-30 | 2026-12-11 | 10 | Domain / Data Architect | 5.1,1.3 | BR-MOR-004,BR-MOR-005,BR-MOR-011 | Gate 5 | Not Started | 0% |  | No
5.3 | Moratorium Management | Build draft creation and evidence workflow | Reason, authority, activity, criteria, period, review, communications and evidence captured | 2026-12-07 | 2026-12-24 | 14 | Frontend / Backend | 5.2,2.5 | BR-MOR-001 | Gate 5 | Not Started | 0% |  | No
5.4 | Moratorium Management | Build impact preview | Affected products, locations, brokers and in-flight transactions estimated before approval | 2026-12-14 | 2027-01-08 | 20 | Backend / Data | 5.2,0.6 | BR-MOR-005,BR-MOR-009 | Gate 5 | Not Started | 0% |  | No
5.5 | Moratorium Management | Build approval and emergency activation | Delegated authority, dual approval, separation of duties and expedited path implemented | 2026-12-21 | 2027-01-15 | 20 | Backend / Frontend | 5.3,2.10 | BR-MOR-002,BR-MOR-003 | Gate 5 | Not Started | 0% |  | No
5.6 | Moratorium Management | Build deterministic evaluation engine | Priority, specificity and conflict rules produce Allow, Suspend or Refer with reason | 2027-01-04 | 2027-01-22 | 15 | Backend Lead | 5.2,5.1 | BR-MOR-006,BR-MOR-007 | Gate 5 | Not Started | 0% |  | No
5.7 | Moratorium Management | Integrate evaluation checkpoints | Rules execute before configured quote, bind, issue and coverage-changing actions | 2027-01-18 | 2027-02-05 | 15 | Backend / Integration | 5.6 | BR-MOR-008,BR-SC-006 | Gate 5 | Not Started | 0% |  | No
5.8 | Moratorium Management | Implement in-flight and existing-business treatment | Draft, submission, quote, bind, renewal, endorsement and in-force rules enforced | 2027-01-18 | 2027-02-05 | 15 | Backend Lead | 5.6 | BR-MOR-009 | Gate 5 | Not Started | 0% |  | No
5.9 | Moratorium Management | Implement controlled exception workflow | Authority, justification, duration, scope and immutable evidence required | 2027-01-25 | 2027-02-12 | 15 | Frontend / Backend | 5.5,5.6 | BR-MOR-010 | Gate 5 | Not Started | 0% |  | No
5.1 | Moratorium Management | Implement lifecycle and complete version history | Activate, extend, narrow, supersede and lift while preserving exact historical criteria | 2027-01-25 | 2027-02-12 | 15 | Backend Lead | 5.5,5.6 | BR-MOR-011,BR-MOR-015 | Gate 5 | Not Started | 0% |  | No
5.11 | Moratorium Management | Implement notifications and communications | Approved broker/internal messages include scope, period and next steps without restricted data | 2027-02-01 | 2027-02-19 | 15 | Frontend / Integration | 5.1 | BR-MOR-012 | Gate 5 | Not Started | 0% |  | No
5.12 | Moratorium Management | Build operations dashboard | Active, scheduled, expiring, lifted, impacted, exceptions and sync status visible | 2027-02-08 | 2027-02-26 | 15 | Frontend / Data | 5.10,5.11 | BR-MOR-013 | Gate 5 | Not Started | 0% |  | No
5.13 | Moratorium Management | Build Duck Creek synchronization and reconciliation | Activation/lifting synchronization, retries, fail-safe and discrepancy handling implemented | 2027-02-01 | 2027-02-26 | 20 | Integration Lead | 0.6,5.10 | BR-MOR-014,NFR-007 | Gate 5 | Not Started | 0% |  | No
5.14 | Moratorium Management | Implement expiry and reauthorization scheduler | Automatic expiry or periodic reapproval with alerts and audit | 2027-02-15 | 2027-02-26 | 10 | Backend Lead | 5.1 | BR-MOR-015 | Gate 5 | Not Started | 0% |  | No
5.15 | Moratorium Management | Implement evaluation audit evidence | Inputs, evaluated rules, determining rule, outcome, actor, channel, time and correlation recorded | 2027-02-15 | 2027-03-05 | 15 | Backend / SRE | 5.6,1.15 | BR-MOR-016 | Gate 5 | Not Started | 0% |  | No
5.16 | Moratorium Management | Execute scenario, boundary and catastrophe-volume tests | Conflicts, exceptions, timing, geography, fail-safe and peak-volume tests pass | 2027-03-01 | 2027-03-19 | 15 | QA / Performance | 5.7,5.8,5.9,5.11,5.12,5.13,5.14,5.15 | BR-MOR-001:BR-MOR-016,NFR-003 | Gate 5 | Not Started | 0% |  | No
5.17 | Moratorium Management | Gate 5: Moratorium controls acceptance | Authorized lifecycle and consistent portal/Duck Creek enforcement approved | 2027-03-22 | 2027-03-22 | 1 | Business Operations / Risk | 5.16 |  | Gate 5 | Not Started | 0% |  | Yes
6.1 | Small Commercial Portal | Finalize configured products, states and transaction scope | Release configuration matrix signed by product, underwriting and compliance | 2027-01-04 | 2027-01-15 | 10 | Product Owner | 0.5,0.6 | BR-SC-001 | Gate 6 | Not Started | 0% |  | No
6.2 | Small Commercial Portal | Design canonical submission lifecycle | Draft through bound/failed state machine, concurrency, ownership and broker visibility approved | 2027-01-11 | 2027-01-22 | 10 | Domain Architect | 1.3,6.1 | BR-SC-002,BR-SC-013,BR-SC-016 | Gate 6 | Not Started | 0% |  | No
6.3 | Small Commercial Portal | Build product discovery and start journey | Authorized product/state selection and create/resume entry implemented | 2027-01-18 | 2027-02-05 | 15 | Frontend / Backend | 2.13,6.1 | BR-SC-001,BR-SC-002 | Gate 6 | Not Started | 0% |  | No
6.4 | Small Commercial Portal | Build draft lifecycle and autosave | Create, save, resume, copy, withdraw, optimistic concurrency and interruption recovery | 2027-01-25 | 2027-02-12 | 15 | Frontend / Backend | 6.2,6.3 | BR-SC-002,BR-SC-016 | Gate 6 | Not Started | 0% |  | No
6.5 | Small Commercial Portal | Build applicant and party management | Search/create insured and contacts with duplicate detection and authority controls | 2027-02-01 | 2027-02-19 | 15 | Frontend / Backend | 6.4,0.7 | BR-SC-004,BR-SC-005 | Gate 6 | Not Started | 0% |  | No
6.6 | Small Commercial Portal | Build dynamic question engine | Effective-dated questions driven by product, state, class, coverage and prior answers | 2027-02-01 | 2027-02-26 | 20 | Frontend / Backend | 6.1,6.2 | BR-SC-003 | Gate 6 | Not Started | 0% |  | No
6.7 | Small Commercial Portal | Build risk, location and exposure intake | Locations, classifications, exposures and operations data captured with validation | 2027-02-15 | 2027-03-05 | 15 | Frontend / Backend | 6.6 | BR-SC-004,BR-SC-005 | Gate 6 | Not Started | 0% |  | No
6.8 | Small Commercial Portal | Build coverage and history intake | Coverages, limits, deductibles, prior insurance and loss details captured | 2027-02-15 | 2027-03-05 | 15 | Frontend / Backend | 6.6 | BR-SC-004,BR-SC-005 | Gate 6 | Not Started | 0% |  | No
6.9 | Small Commercial Portal | Integrate producer authority and eligibility controls | Appointment, license, territory, product and transaction authority validated | 2027-02-22 | 2027-03-12 | 15 | Backend / Integration | 0.7,6.5 | BR-AUTH-005,BR-SC-005 | Gate 6 | Not Started | 0% |  | No
6.1 | Small Commercial Portal | Integrate moratorium controls into journey | Re-evaluation occurs on material risk, location, coverage and effective-date changes | 2027-03-08 | 2027-03-19 | 10 | Backend Lead | 5.7,6.7,6.8 | BR-SC-006 | Gate 6 | Not Started | 0% |  | No
6.11 | Small Commercial Portal | Build document collection and scanning | Type, size, content and malware validation with metadata, version and secure transfer | 2027-02-22 | 2027-03-12 | 15 | Frontend / Backend | 6.4 | BR-SC-007,NFR-004 | Gate 6 | Not Started | 0% |  | No
6.12 | Small Commercial Portal | Build completeness and cross-field validation | Required, format, consistency, duplicate and business-rule validation with clear recovery | 2027-03-01 | 2027-03-19 | 15 | Backend / Frontend | 6.7,6.8,6.11 | BR-SC-005 | Gate 6 | Not Started | 0% |  | No
6.13 | Small Commercial Portal | Build role-scoped search and dashboard | Draft, submission, quote and policy searches honor agency and role data scopes | 2027-03-01 | 2027-03-19 | 15 | Frontend / Backend | 6.4,2.5 | BR-SC-015 | Gate 6 | Not Started | 0% |  | No
6.14 | Small Commercial Portal | Build Duck Creek submission adapter | Create/update submission with correlation, downstream IDs, idempotency and trackable status | 2027-03-08 | 2027-03-26 | 15 | Integration Lead | 0.6,6.12 | BR-SC-008,BR-SC-014 | Gate 6 | Not Started | 0% |  | No
6.15 | Small Commercial Portal | Build rating request and quote presentation | Approved premium, taxes, fees, coverages, limits, forms, conditions and expiry displayed | 2027-03-22 | 2027-04-09 | 15 | Integration / Frontend | 6.14 | BR-SC-009,BR-SC-010 | Gate 6 | Not Started | 0% |  | No
6.16 | Small Commercial Portal | Build referral and information-request workflow | Underwriting routing, ownership, SLA, status and broker notifications implemented | 2027-03-22 | 2027-04-09 | 15 | Frontend / Backend | 6.14 | BR-SC-011 | Gate 6 | Not Started | 0% |  | No
6.17 | Small Commercial Portal | Build bind and issue flow | Authority, completeness, payment/document prerequisites, moratorium and downstream validation enforced | 2027-04-05 | 2027-04-23 | 15 | Integration / Backend | 6.15,6.16,5.17 | BR-SC-012 | Gate 6 | Not Started | 0% |  | No
6.18 | Small Commercial Portal | Build broker-safe status timeline | Documents, messages, decisions and transaction history exclude restricted internal detail | 2027-03-29 | 2027-04-16 | 15 | Frontend / Backend | 6.14,6.16 | BR-SC-013 | Gate 6 | Not Started | 0% |  | No
6.19 | Small Commercial Portal | Implement comparative-rater deep links | Signed state, authentication, integrity, expiry and replay protection implemented | 2027-04-05 | 2027-04-16 | 10 | Security / Integration | 2.13,6.3 | BR-SC-018 | Gate 6 | Not Started | 0% |  | No
6.2 | Small Commercial Portal | Implement end-to-end submission audit | Material actions and downstream outcomes recorded with correlation and privacy controls | 2027-04-05 | 2027-04-23 | 15 | Backend / SRE | 6.14,1.15 | BR-SC-017 | Gate 6 | Not Started | 0% |  | No
6.21 | Small Commercial Portal | Execute Small Commercial integration and journey tests | All 12 journey stages, negative paths, authorization and duplicate-prevention tests pass | 2027-04-19 | 2027-05-07 | 15 | QA Lead | 6.10,6.11,6.12,6.13,6.15,6.16,6.17,6.18,6.19,6.20 | BR-SC-001:BR-SC-018 | Gate 6 | Not Started | 0% |  | No
6.22 | Small Commercial Portal | Gate 6: Small Commercial functional acceptance | Configured product journey passes from authenticated start through approved bind/issue and tracking | 2027-05-10 | 2027-05-10 | 1 | Product / Underwriting | 6.21 |  | Gate 6 | Not Started | 0% |  | Yes
7.1 | Integration, Data & Operations | Implement integration outbox and async processing | Trackable long-running operations, outbox, retries and dead-letter handling implemented | 2027-01-18 | 2027-02-05 | 15 | Integration Lead | 1.13,1.14 | NFR-007 | Gate 7 | Not Started | 0% |  | No
7.2 | Integration, Data & Operations | Implement API idempotency and concurrency controls | Retry-sensitive writes prevent duplicates and enforce explicit version checks | 2027-02-01 | 2027-02-19 | 15 | API Lead | 1.4,7.1 | BR-SC-014,NFR-007 | Gate 7 | Not Started | 0% |  | No
7.3 | Integration, Data & Operations | Implement timeout, circuit breaker and degradation policies | External dependency failures produce safe recoverable states | 2027-02-08 | 2027-02-26 | 15 | Integration Lead | 7.1 | NFR-007 | Gate 7 | Not Started | 0% |  | No
7.4 | Integration, Data & Operations | Build reconciliation framework | Identity, submission and moratorium discrepancies detected, owned and repairable | 2027-02-15 | 2027-03-05 | 15 | Integration / SRE | 7.1,7.2 | BR-AUTH-010,BR-MOR-014,BR-SC-014 | Gate 7 | Not Started | 0% |  | No
7.5 | Integration, Data & Operations | Build notification service | Email and in-app events, templates, preferences and delivery status implemented | 2027-02-15 | 2027-03-05 | 15 | Backend Lead | 1.13 | BR-AI-008,BR-MOR-012,BR-SC-011 | Gate 7 | Not Started | 0% |  | No
7.6 | Integration, Data & Operations | Build immutable audit service | Actor, time, action, object, versions, outcome, channel, reason and correlation captured | 2027-02-15 | 2027-03-12 | 20 | Backend / Security | 1.14,1.15 | BR-AUTH-009,BR-AI-010,BR-MOR-016,BR-SC-017 | Gate 7 | Not Started | 0% |  | No
7.7 | Integration, Data & Operations | Build business reporting datasets | Adoption, guideline, moratorium, conversion, referral and failure metrics available | 2027-03-15 | 2027-04-02 | 15 | Data Engineer | 7.4,7.6 | NFR-009 | Gate 7 | Not Started | 0% |  | No
7.8 | Integration, Data & Operations | Build operational dashboards and alerts | Identity, Duck Creek, indexing, moratorium, app, DB, capacity and security views active | 2027-03-15 | 2027-04-09 | 20 | SRE / Data | 7.4,1.15 | NFR-009 | Gate 7 | Not Started | 0% |  | No
7.9 | Integration, Data & Operations | Create tiered support model and ownership matrix | L1/L2/L3 responsibilities, service hours, escalation and communications approved | 2027-03-22 | 2027-04-02 | 10 | Support Lead | 0.12 |  | Gate 7 | Not Started | 0% |  | No
7.1 | Integration, Data & Operations | Create operational runbooks | Login, provisioning, stuck submission, duplicates, AI issue, moratorium and outage runbooks tested | 2027-04-05 | 2027-04-23 | 15 | Support / SRE | 7.8,7.9 |  | Gate 7 | Not Started | 0% |  | No
7.11 | Integration, Data & Operations | Implement safe support tooling | Delegated access, reason capture, bounded repair actions and audit evidence | 2027-04-05 | 2027-04-23 | 15 | Support Engineering | 2.10,7.6 |  | Gate 7 | Not Started | 0% |  | No
7.12 | Integration, Data & Operations | Gate 7: Operational readiness baseline | Dashboards, alerts, reconciliation, support ownership and runbooks approved | 2027-04-26 | 2027-04-26 | 1 | Operations Review Board | 7.7,7.8,7.10,7.11 |  | Gate 7 | Not Started | 0% |  | Yes
8.1 | Quality & Release | Finalize master test strategy and data plan | Functional, negative, contract, E2E, security, accessibility, performance and DR coverage approved | 2027-01-11 | 2027-01-22 | 10 | Test Manager | 0.13,1.5,1.7 |  | Gate 8 | Not Started | 0% |  | No
8.2 | Quality & Release | Automate unit and component tests | Approved code coverage and quality gates enforced in CI | 2027-01-25 | 2027-04-23 | 65 | Engineering Leads | 8.1,1.10 | NFR-010 | Gate 8 | Not Started | 0% |  | No
8.3 | Quality & Release | Automate API contract and compatibility tests | Portal and Duck Creek contracts validated for supported versions | 2027-02-08 | 2027-04-23 | 55 | QA / Integration | 0.6,8.1 |  | Gate 8 | Not Started | 0% |  | No
8.4 | Quality & Release | Execute system integration testing | Cross-module identity, AI, moratorium, submission and operations flows pass | 2027-05-03 | 2027-05-14 | 10 | QA Lead | 4.13,5.17,6.21,7.12 | BR-AUTH-001:BR-SC-018 | Gate 8 | Not Started | 0% |  | No
8.5 | Quality & Release | Execute security and privacy testing | SAST/DAST, API, authorization, data leakage, file and privacy controls meet gate | 2027-05-03 | 2027-05-21 | 15 | Security / Privacy | 8.2,8.3,4.12,6.21 | NFR-004,NFR-005,NFR-012 | Gate 8 | Not Started | 0% |  | No
8.6 | Quality & Release | Execute accessibility and compatibility testing | WCAG 2.2 AA and approved browser/device/assistive matrix results accepted | 2027-05-10 | 2027-05-21 | 10 | Accessibility QA | 6.21 | NFR-006,NFR-011 | Gate 8 | Not Started | 0% |  | No
8.7 | Quality & Release | Execute performance and catastrophe-volume testing | p95 targets, concurrency, content and catastrophe peaks meet approved thresholds | 2027-05-10 | 2027-05-28 | 15 | Performance QA | 5.16,6.21,7.8 | NFR-002,NFR-003 | Gate 8 | Not Started | 0% |  | No
8.8 | Quality & Release | Execute resilience and recovery testing | Timeouts, retries, failover, reconciliation, backup restore and RTO/RPO validated | 2027-05-17 | 2027-05-28 | 10 | SRE / QA | 7.3,7.4,7.10 | NFR-007,NFR-008 | Gate 8 | Not Started | 0% |  | No
8.9 | Quality & Release | Complete UAT readiness and training | UAT scripts, users, test data, training and environment approved | 2027-05-17 | 2027-05-28 | 10 | Business Test Lead | 8.4 |  | Gate 8 | Not Started | 0% |  | No
8.1 | Quality & Release | Execute business UAT | Broker, admin, underwriter, operations and support scenarios accepted | 2027-05-31 | 2027-06-11 | 10 | Business Users | 8.5,8.6,8.7,8.8,8.9 |  | Gate 8 | Not Started | 0% |  | No
8.11 | Quality & Release | Resolve defects and run regression | Release candidate meets severity, regression and traceability exit criteria | 2027-06-07 | 2027-06-18 | 10 | Engineering / QA | 8.1 |  | Gate 8 | Not Started | 0% |  | No
8.12 | Quality & Release | Complete production readiness review | Security, privacy, architecture, data, support, DR, monitoring and release evidence approved | 2027-06-14 | 2027-06-18 | 5 | Release Manager | 8.11,7.12 |  | Gate 8 | Not Started | 0% |  | No
8.13 | Quality & Release | Gate 8: Go-live approval | SteerCo approves release scope, residual risk, rollback and cutover | 2027-06-21 | 2027-06-21 | 1 | Steering Committee | 8.12 |  | Gate 8 | Not Started | 0% |  | Yes
8.14 | Quality & Release | Execute production cutover | Deploy application, database, configuration, content index and integrations per runbook | 2027-06-22 | 2027-06-23 | 2 | Release / DevOps | 8.13 |  | Gate 8 | Not Started | 0% |  | No
8.15 | Quality & Release | Execute production smoke and reconciliation | Authentication, search, AI, moratorium, submission and monitoring smoke tests pass | 2027-06-24 | 2027-06-25 | 2 | QA / SRE | 8.14 |  | Gate 8 | Not Started | 0% |  | No
8.16 | Quality & Release | Production go-live milestone | Broker Portal Release 1 opened to approved users | 2027-06-28 | 2027-06-28 | 1 | Product Owner | 8.15 |  | Gate 8 | Not Started | 0% |  | Yes
9.1 | Hypercare & Closure | Operate hypercare command center | Daily operational review, incident triage, business communications and metric tracking | 2027-06-28 | 2027-07-09 | 10 | Support / Product | 8.16 |  | Gate 9 | Not Started | 0% |  | No
9.2 | Hypercare & Closure | Monitor adoption and service objectives | Login, AI, moratorium, submission, latency, errors and capacity reviewed against baseline | 2027-06-28 | 2027-07-09 | 10 | SRE / Product | 8.16 | NFR-001,NFR-002,NFR-003,NFR-009 | Gate 9 | Not Started | 0% |  | No
9.3 | Hypercare & Closure | Resolve priority production defects | Critical/high incidents resolved or accepted with approved remediation plan | 2027-06-28 | 2027-07-09 | 10 | Engineering Leads | 8.16 |  | Gate 9 | Not Started | 0% |  | No
9.4 | Hypercare & Closure | Complete post-production access and audit review | Privileged access, audit completeness and support actions reviewed | 2027-07-05 | 2027-07-09 | 5 | Security / Audit | 8.16 | BR-AUTH-009,BR-SC-017 | Gate 9 | Not Started | 0% |  | No
9.5 | Hypercare & Closure | Transition to steady-state support | Knowledge transfer, backlog ownership, SLAs and on-call responsibilities accepted | 2027-07-08 | 2027-07-14 | 5 | Support Lead | 9.1,9.3 |  | Gate 9 | Not Started | 0% |  | No
9.6 | Hypercare & Closure | Complete lessons learned and benefits baseline | Delivery retrospective and success-measure baseline documented | 2027-07-12 | 2027-07-15 | 4 | Program Manager | 9.1,9.2 |  | Gate 9 | Not Started | 0% |  | No
9.7 | Hypercare & Closure | Gate 9: Hypercare exit and project closure | Steady-state owners accept service and sponsor closes implementation | 2027-07-16 | 2027-07-16 | 1 | Sponsor / Operations | 9.4,9.5,9.6 |  | Gate 9 | Not Started | 0% |  | Yes
Formulas:
Workdays = NETWORKDAYS([Start Date],[End Date])

## Project Overview
BHSI Broker Portal — End-to-End Implementation Plan
Baseline: 01 Oct 2026 to 16 Jul 2027 ¦ Auth0, AI Guidelines, Moratoriums, Small Commercial, Duck Creek and operations
Executive KPI | Value |  | Schedule KPI | Value
Detailed activities | 140 |  | Baseline start | 2026-10-01
Requirement records | 68 |  | Production go-live | 2027-06-28
Milestones | 11 |  | Hypercare exit | 2027-07-16
Open risks / decisions | 18 |  | Planned completion | 0%
Gate | Target Date | Outcome | Accountable Body
Gate 0 | 2026-10-21 | Discovery, scope and delivery baseline approved | Steering Committee
Gate 1 | 2026-11-16 | Architecture and platform ready | Architecture Review Board
Gate 2 | 2027-01-11 | Identity and access accepted | Product Owner / Security
Gate 3 | 2027-01-25 | Guideline content and search accepted | Guideline Product Owner
Gate 4 | 2027-03-08 | AI assistant accepted | AI Governance Board
Gate 5 | 2027-03-22 | Moratorium controls accepted | Business Operations / Risk
Gate 6 | 2027-05-10 | Small Commercial journey accepted | Product / Underwriting
Gate 7 | 2027-04-26 | Operational readiness baseline accepted | Operations Review Board
Gate 8 | 2027-06-28 | Production go-live | Steering Committee
Gate 9 | 2027-07-16 | Hypercare exit and closure | Sponsor / Operations
Critical delivery assumptions
1. Angular, ASP.NET Core, SQL Server and Auth0 remain the approved technology direction.
2. Duck Creek remains system of record; unsupported capabilities are not assumed before contract approval.
3. Identity, AI, Moratorium and Small Commercial squads execute in parallel after the shared platform gate.
4. Product/state scope, NFR targets and bind/issue capability are approval gates, not silent assumptions.
5. Re-baseline dates after Gate 0 using confirmed team capacity and external dependency commitments.
Source: BHSI_Broker_Portal_Business_and_System_Requirements v.1.0, modified 24 Sep 2026.
Formulas:
Value = MIN(tblBrokerPortalPlan[Start Date])
Value = MAXIFS(tblBrokerPortalPlan[End Date],tblBrokerPortalPlan[WBS],"8.16")

## Requirements Traceability
Requirement ID | Domain | Requirement Summary | Planned WBS | Acceptance Evidence | Accountable Owner | Status | Release Gate
BR-AUTH-001 | Identity | Auth0-mediated external broker sign-in | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-002 | Identity | Approved broker identity-provider federation | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-003 | Identity | Approved internal enterprise identity | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-004 | Identity | User mapped to organization, agency or branch | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-005 | Identity | Server-side roles, permissions, entitlements and ownership | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-006 | Identity | Broker administrator lifecycle management within scope | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-007 | Identity | Provision or synchronize Auth0, portal and Duck Creek users | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-008 | Identity | MFA, lockout, timeout, logout and revocation | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-009 | Identity | Audit identity lifecycle and privileged access | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AUTH-010 | Identity | Visible, recoverable partial provisioning | 2.1-2.12 | Identity functional, authorization, negative-path and reconciliation tests | IAM / Security | Planned | Gate 2
BR-AI-001 | AI Guidelines | Upload approved guideline formats | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-002 | AI Guidelines | Review and publish before end-user access | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-003 | AI Guidelines | Natural-language questions with applicability filters | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-004 | AI Guidelines | Ground answers in authorized content | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-005 | AI Guidelines | Show source, locator, version and effective date | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-006 | AI Guidelines | Refuse or escalate weak, conflicting or stale evidence | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-007 | AI Guidelines | No final underwriting, pricing, bind, issue, legal or regulatory decision | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-008 | AI Guidelines | Capture user feedback | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-009 | AI Guidelines | Publish, supersede, retire and re-index with audit | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-010 | AI Guidelines | Retain privacy-safe interaction record | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-011 | AI Guidelines | Defend against prompt injection and disclosure | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-AI-012 | AI Guidelines | Display informational-use notice | 3.1-4.12 | Content lifecycle, Q&A quality, citation, refusal and AI-security evidence | AI / Underwriting | Planned | Gate 4
BR-MOR-001 | Moratorium | Create draft with reason, authority, scope, period and evidence | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-002 | Moratorium | Approval and separation-of-duties rules | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-003 | Moratorium | Emergency activation with expedited approval | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-004 | Moratorium | Explicit affected insurance activities | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-005 | Moratorium | Product, geography, peril, risk and distribution criteria | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-006 | Moratorium | Effective-dated precedence and conflict rules | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-007 | Moratorium | Allow, Suspend or Refer with explanation | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-008 | Moratorium | Evaluate and re-evaluate before affected transactions | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-009 | Moratorium | Treatment of in-flight and existing business | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-010 | Moratorium | No bypass; governed exception evidence | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-011 | Moratorium | Complete lifecycle version history | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-012 | Moratorium | Approved internal and broker communications | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-013 | Moratorium | Operational views and synchronization status | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-014 | Moratorium | Duck Creek synchronization, reconciliation and fail-safe | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-015 | Moratorium | Automatic expiry or periodic reauthorization | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-MOR-016 | Moratorium | Complete evaluation audit inputs and outcome | 5.1-5.16 | Decision-table, lifecycle, integration, audit and catastrophe-volume evidence | Operations / Risk | Planned | Gate 5
BR-SC-001 | Small Commercial | Configured products and states by release | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-002 | Small Commercial | Create, save, resume, copy and withdraw drafts | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-003 | Small Commercial | Dynamic questions by product and risk context | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-004 | Small Commercial | Capture applicant, producer, location, exposure, coverage and history | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-005 | Small Commercial | Required, format, consistency, duplicate and business validation | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-006 | Small Commercial | Evaluate active moratoriums before configured transactions | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-007 | Small Commercial | Secure document validation, scanning and transmission | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-008 | Small Commercial | Create or update Duck Creek submissions with correlation IDs | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-009 | Small Commercial | Request rating and present role-approved details | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-010 | Small Commercial | Display authoritative quote versions and terms | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-011 | Small Commercial | Referral and information-request workflow | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-012 | Small Commercial | Governed bind and issue actions | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-013 | Small Commercial | Broker-safe status timeline | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-014 | Small Commercial | Idempotency and reconciliation prevent duplicate transactions | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-015 | Small Commercial | Role-appropriate search | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-016 | Small Commercial | Autosave, conflict handling and session recovery | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-017 | Small Commercial | Audit material actions and downstream outcomes | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
BR-SC-018 | Small Commercial | Secure comparative-rater deep links | 6.1-6.21 | Journey, contract, duplicate-prevention, authorization and UAT evidence | Product / Integration | Planned | Gate 6
NFR-001 | NFR | 99.9% target availability subject to approval | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-002 | NFR | Approved p95 targets for key interactions | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-003 | NFR | Scale for users, content and catastrophe peaks | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-004 | NFR | TLS, headers, CSP, CORS, secrets and security scanning | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-005 | NFR | Privacy minimization, retention, deletion and restricted support | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-006 | NFR | WCAG 2.2 AA target | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-007 | NFR | Timeouts, circuit breakers, retries, idempotency and reconciliation | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-008 | NFR | Approved RTO/RPO before UAT | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-009 | NFR | Logs, metrics, traces, audit, dashboards and correlation | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-010 | NFR | Modular design, automated tests, quality gates and documentation | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-011 | NFR | Approved browser, device, file and assistive-technology matrix | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8
NFR-012 | NFR | AI grounding, citations, security, evaluation and rollback | 0.12,1.1-8.12 | Approved NFR baseline plus specialist test and production-readiness evidence | Architecture / SRE | Planned | Gate 8

## RAID & Decisions
ID | Type | Risk / Decision | Impact | Probability / Urgency | Mitigation / Required Outcome | Owner | Status | Linked WBS
R-001 | Risk | Duck Creek APIs, environments, authentication, contracts or limits unknown | High | Medium | Complete integration discovery and contract tests before commitment | Integration Architect | Open | 0.6
R-002 | Risk | Identity or entitlement synchronization becomes stale | High | Medium | Define authority, event/reconciliation model, revocation and fail-safe behavior | IAM Architect | Open | 0.7,2.8,2.11
R-003 | Risk | AI returns unsupported or outdated guidance | High | Medium | Use approved content lifecycle, citations, evaluation, refusal, monitoring and rollback | AI Product Owner | Open | 3.1-4.13
R-004 | Risk | Incorrect or delayed moratorium enforcement permits prohibited activity or blocks allowed business | High | Medium | Use precise scope, deterministic precedence, synchronized enforcement, fail-safe and reconciliation | Operations Lead | Open | 5.1-5.17
R-005 | Risk | Headless workflow duplicates or loses downstream transactions | High | Medium | Use idempotency, correlation, state machine, retries and reconciliation | Integration Lead | Open | 6.14,7.1-7.4
R-006 | Risk | Sensitive guideline or broker data is exposed | High | Medium | Apply access filtering, secure retrieval, minimization, testing and monitoring | Security Lead | Open | 1.5,1.6,4.8,8.5
R-007 | Risk | Catastrophe event creates traffic spikes | High | Medium | Capacity modeling, load tests, scaling and operational playbooks | SRE Lead | Open | 5.16,8.7
R-008 | Risk | MVP expands to all policy-lifecycle transactions | High | Medium | Use release-based scope and formal change control | Product Owner | Open | 0.5
OD-001 | Decision | Release 1 products, states, stages and personas | High | Urgent | Approve Release 1 scope matrix | Product Owner | Due | 0.5
OD-002 | Decision | Duck Creek products, versions and approved APIs/services | High | Urgent | Approve integration catalogue | Duck Creek Owner | Due | 0.6
OD-003 | Decision | Authority for broker, agency, producer and entitlements | High | Urgent | Approve source-of-truth and synchronization design | Data Owner | Due | 0.7
OD-004 | Decision | Auth0 tenant, organization, MFA, session and invitation policies | High | Urgent | Approve IAM design | IAM Owner | Due | 0.8
OD-005 | Decision | AI model, search/vector, repository, moderation and retention services | High | Urgent | Approve AI platform design | AI Governance | Due | 0.9
OD-006 | Decision | Guideline owners, approvals, effective dates and emergency corrections | High | Urgent | Approve content governance | Underwriting Owner | Due | 0.1
OD-007 | Decision | Moratorium authority store, Duck Creek sync and outage behavior | High | Urgent | Approve moratorium architecture | Operations / Duck Creek | Due | 0.11
OD-008 | Decision | Moratorium scope, precedence, exceptions, communications and lifting | High | Urgent | Approve operating rulebook | Operations / Risk | Due | 0.11
OD-009 | Decision | Available rating, quote, referral, bind, issue, document and payment journeys | High | Urgent | Approve capability matrix | Duck Creek / Product | Due | 0.6
OD-010 | Decision | Volumes, SLOs, RTO/RPO, retention and support hours | High | Urgent | Approve NFR baseline | Architecture / Operations | Due | 0.12